## Slide 1
ONEIDA
RECREATION AND FITNESS COMPLEX

## Slide 2
RECREATION
COMPLEX
The Oneida Nation Recreation Complex is a project to provide a centrally located, state-of-the-art recreational complex that supports the social, cultural, physical, and recreational needs of the Oneida Community.
A new recreation complex would provide improved access and convenience to tribal members, increased programming and service capacity, increased synergy with the tribal schools, departments, and community.

## Slide 3
RECREATION COMPLEX
ONEIDA
CDC #16-011
Project Team:
  Sam Van Den Heuvel SR Construction Manager - Engineering Dept.
  Paul J. Witek Engineering Director/Senior Architect
  Troy D. Parr Area Manager - DPW - Community Development
  Shannon Stone Director of DPW
  Tina Jorgensen HSD Division Director
  Arlouine Bain Recreation Director
  Ryan Waterstreet Oneida Family Fitness Director
  Presley A. Cornelius Office Manager Recreation
  Amy Griesbach Member Services Manager

## Slide 4
THREE POTENTIAL SITES
CAMPUS PROJECT
The new Recreation Complex provides the opportunity for the community to have one central hub located in Central Oneida for all their fitness & recreational activities. This would also serve as a safe shelter for the community in times of emergency/natural disaster.

## Slide 5
WHY A NEW FACILITY?
  Both Recreation and Fitness have outgrown their current facilities.
  Spaces have become too small for existing programs and community needs.
  Inoperable pool area.
  Do not have the flexibility for diverse programming needs.
  No on-site childcare.
  Non-compliant ropes course.
  Lack of storage space at both facilities.
  Not elderly friendly.
  The lack of athletic fields for adequate programming of games and tournaments.
  The lack of gymnasium space to host tournaments.
  To bring Recreation and Fitness together in one facility.

## Slide 6
PROJECT COST ESTIMATE: OPTION #1 WITH AQUATICS
SOFT and MISCELLANEOUS COSTS
  Engineering Dept. Fees
  Architect / Engineer Fees & Reimbursables
  Commissioning
  Soil Borings, Testing, and Surveys
  Agency Review and Approval Fees
  Insurance - Builders Risk
  Historical/Cultural/Archaeological Review
789,000
4,709,000
673,000
74,000
67,000
covered by property insurance
2,000
CONSTRUCTION
  Utility Relocation/Extension
  Site Work & Landscape
  Building Construction & General Conditions
  Playing Fields
  Oneida Preference Amount
  Sustainable Design Premium 3.5%
  Inflation Factor: 2 years 5% per year
1,511,000
5,037,000
50,368,000
1,854,000
58,770,000
193,000
2,057,000
6,255,000
Sub-Total:
Sub-Total:
6,314,000
Sub-Total:
67,275,000
FIXTURES, FURNISHINGS, AND EQUIPMENT
  Division 10 - Specialties
  Division 11/12 - Equipment & Furnishings
  Division 27 - Communications
  Division 28 - Electronic Safety & Security
925,000
3,364,000
1,175,000
661,000
Sub-Total:
6,125,000
TOTAL:
Contingency:
Finance Costs:
10.0%
0.0%
79,714,000
7,971,000
0
Estimated Total Project Budget:
$87,685,000

## Slide 7
PROJECT COST ESTIMATE: OPTION #2 WITHOUT AQUATICS
SOFT and MISCELLANEOUS COSTS
  Engineering Dept. Fees
  Architect / Engineer Fees & Reimbursables
  Commissioning
  Soil Borings, Testing, and Surveys
  Agency Review and Approval Fees
  Insurance - Builders Risk
  Historical/Cultural/Archaeological Review
577,000
3,465,000
495,000
54,000
50,000
covered by property insurance
2,000
CONSTRUCTION
  Utility Relocation/Extension
  Site Work & Landscape
  Building Construction & General Conditions
  Playing Fields
  Oneida Preference Amount
  Sustainable Design Premium 3.5%
  Inflation Factor: 2 years 5% per year
1,099,000
3,663,000
36,625,000
1,854,000
43,241,000
146,000
1,980,000
4,602,000
Sub-Total:
Sub-Total:
4,643,000
Sub-Total:
49,502,000
FIXTURES, FURNISHINGS, AND EQUIPMENT
  Division 10 - Specialties
  Division 11/12 - Equipment & Furnishings
  Division 27 - Communications
  Division 28 - Electronic Safety & Security
744,000
1,980,000
994,000
425,000
Sub-Total:
4,143,000
TOTAL:
Contingency:
Finance Costs:
10.0%
0.0%
58,288,000
5,829,000
0
Estimated Total Project Budget:
$64,117,000

## Slide 8
PROJECT FINANCIAL PLAN
COMMUNICATION PLAN
A. Tribal Financing: - It is proposed to fund this project through the tribal CIP Budget.
B. As the project is a very large capital costs, it is assumed the funding allocation would be included in multiple fiscal year CIP budgets. The approved FY2023 CIP Budget includes an allocation of $250,000 for this project. Additional project funds will be requested as follows:
C. The Project Team has been researching possible grant opportunities for the project.
FY2024 CIP Budget:
FY2025 CIP Budget:
FY2026 CIP Budget:
$7,487,000
$45,407,000
$34,541,000
$5,424,000
$33,127,000
$25,316,000
Option #1
Option #2
A. Information included in a communication plan for this project will include:
  CIP Project number
  Project title
  Brief description of the project story and scope
  Images of similar type facilities
  Project schedule
  Financial Plan
B. The Project Information will be communicated to the community and staff as follows:
  Reports on Oneida website (Project Manager)
  Groundbreaking and dedication ceremonies scheduled with the events coordinator (Project Manager/Business Unit Manager)
  Periodic articles in the Kalihwisaks based upon the specific needs of the project (Project Manager)

## Slide 9
WHAT WE KNOW
  Both facilities are limited in what can be offered to the youth & elders
  The current Recreation building has outlived its life span of 40 years.
  Storage is not adequate for supplies needed for youth events.
  If we keep using the Civic Center for our youth, we will constantly be needing to spend money year after year. Estimates are below:
    Roof replacement - $165,000
    Upgrade plumbing - $200,000
    Exterior masonry wall repairs - $15,000
  The current Fitness Center building is multi-level making it inconvenient for Elders and youth as well as individuals with special needs.
  The current Fitness Center building no longer has an Aquatics Area for members to utilize/exercise.
  The Fitness Center Elevator continues to need continued maintenance.

## Slide 10
THANK YOU